## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
CCTV (Assessment & Implementation) Policy | Policy | To provide guidance in relation to the assessment and installation of Council-owned or operated CCTV systems. · It explains the role of CCTV systems, with Councils place-based, community activation, and engagement context, as compared to more traditional crime and justice settings. · It explains how Council will make balanced decisions about the installation of CCTV systems, against its commitment to improving the overall quality of life of people in the local community, and its role in maintaining the peace, order, and good government of the municipal area. | New | Yes | It appeared that youth at skatepark were the only ones not in support of cameras citing that they would lose their privacy. This consequence does not outweigh the safety benefits of having the cameras in place. While CCTV is a responsive measure, it is hoped that women and gender-diverse people feel safer being in public spaces that have CCTV cameras. | Yes
Fair Access Policy | Policy | The Fair Access Policy (the Policy) seeks to address known barriers experienced by women and girls in accessing and using community sports infrastructure. The Policy aims to progressively build capacity and capabilities of Ararat Rural City Council (Council) in the identification, and elimination of systemic causes of gender inequality in policy, programs, communications, and delivery of services in relation to community sports infrastructure. | New | Yes | The aim of this policy is to create and embed equality amongst our community. The Policy is targeted at the following groups: Local sporting clubs, Ararat Rural City residents, Committees of Management of recreation reserves, new sporting clubs, sport and recreation staff within Council | Yes
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Relevant indicator(s) 1: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and pratices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
Challenge the gender stereotyping of roles in our workplace, encouraging and celebrating diversity no matter what the role is. | Ongoing | Change any gendered language in our recruitment practices & Improve recruitment methods to encourage all people to apply regardless of gender | A successful evaluation of gender-inclusive recruitment practices involved an examination of language modification, outreach effectiveness, and the overall encouragement of individuals of all genders to apply.By analyzing feedback, participation rates, and application trends, Council can gauge the success of our efforts in creating a more incluise and equal opportunity recruitment process. Regular assessments and adjustments are crucial for maintaining progress and ensuring sustained inclusivity. | 2022 | Paula Davidson - Human Resource Business Partner | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1
Incorporate gender equality, diversity and inclusion in plans, frameworks, and strategies as they are reviewed. | Ongoing | Challenge and change any gendered language in our publications, policies, and procedures. |  | 2022 | Josie Frawley - Executive Officer & Sarah Benkhauser - Media | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 2
Role model a commitment to women in leadership and diversity, within the organisation and with business partners. | Complete | Increase the visibility of women and people of diverse genders in leaderships roles | Women hold many senior roles within ARCC, particularly in the indoor staff section. The following senior officer roles are filled by women: Deputy CEO, Human Resource Business Partner, Organisational Transformation Specialist, Financial Services Coordinator, Rates & Valuation Officer, Executive Officer, Governance & Risk Lead and Contracts & Procurement Lead. | 2022 | Paula Davidson - Human Resource Business Partner | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 2
Support and encourage women and people of diverse genders to consider and run for election | Not started | Promote the benefits of running for Council & Encourage the community to attend Council meetings to get a taste of what they could be involved in | With the election coming up in October 2024, ARCC plan to do more work than ever to encourage women and people of diverse genders to consider becoming a Coumcillor. Information sessions will be run for the community, and their will be specific info sessions for women, hosted by previous Mayor - Cr Jo Armstrong (current Coucnillor) | 2022 | Josie Frawley - Executive Officer & Dr Tim Harrison - Chief Executive Officer | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 2
Build awareness and understanding of the key concepts and issues surrounding pay equity. | Ongoing | Unconscious bias training for those in leadership positions and recruitment panels | Unconscious bias training conducted for all staff including those with leadership positions. Recruitment panels still be implemented. | 2022 | Paula Davidson - Human Resource Business Partner | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 3
Actively seek to reduce the gender pay gap. | Ongoing | Conduct an annual gender pay equity audit, analysing and addressing any discrepancies & ensure remuneration is determined prior to advertising | The success of the gender pay audit and pre-advertisement remuneration practices can be measured through the thoroughness of audits, the effectiveness of discrepancy resolution, policy implementation, and the overall satisfaction and perception of employees. Regular monitoring, transparent communication, and a commitment to addressing any identified issues are crucial components of a successful evaluation. By continuously assessing and adapting these initiatives, Council can foster a culture of fairness, equality and inclusivity. | 2022 | Paula Davidson - Human Resource Business Partner | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 3
An inclusive workplace where we: 1. Learn from each other. 2 Don’t make excuses for others demonstrating negative behaviours. 3. Start the conversation about respectful workplace behaviours. 4. Start speaking up when we witness bad behaviour. No matter the setting or context we will all use respectful language and behaviours. | Ongoing | Incorporate these conversations into day-to-day work practices, team/OHS/tool-box meetings to normalise and embed these concepts and conversations | Overall, success in not only demonstrated through specific actions but also reflected in the overall organisational culture. A truly inclusive workplace exhibits a sense of belonging, mutual respect, and continuous improvement in behaviours and attitudes. Ongoing monitoring, feedback mechanisms, and a commitment to addressing challenges are essential for sustaining and enhancing this success over time. | 2022 | Consultative Committee | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Show leadership through our actions and have the skills to challenge negative behaviours. | Complete | All staff to undertake Active Bystander Training & All supervisors to be trained in how to respond to disclosures of sexual harassment and other negative behaviours | This training was completed through Women's Health Grampians. On a daily basis we are seeing staff become more intuned with the language they use and how they conduct themselves at work. | 2022 | All senior staff | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Create a culture that supports staff to seek the flexibility they need. (Stop assuming that work times and conditions are fixed just because that’s how they have always been) | Ongoing | Incorporate these conversations into day-to-day work practices, team/OHS/tool-box meetings to normalise and embed these concepts and conversations & Policies and processes that are accessible and easily understood by all staff | Policies within ARCC are updated on a regular basis. As policies are coming up for review, we are working with the relevant responsible officer for that policy, to ensure that the lanague used throughout the policy is accessible, easily understood and gender neutral | 2022 | Ian Cooper - Depot Coordinator & Paula Davidson - Human Resource Business Partner | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Support women, men, and gender diverse people to increase their working hours, if they choose, whilst gaining a greater understanding of the barriers that may prevent them from doing so. | Not started | Before we advertise, analyse the current workforce in an effort to utilise the talent we already have & Incorporate these conversations, asking questions during day-to-day work practices and one-on-one meetings to normalise and understand individual circumstances | Success in supporting women, men and gender-diverse people to increase their working hours involves a combination of volunary choices, understanding and addressing barriers, fostering an inclusive culture, promoting well-being, providing professional development opportunites, ensuring retention, and maintaining equitable policies and practices. Regular assessments and adjustments to programs based on feedback and changing needs are essential for sustained succes to this strategy. | 2022 | Paula Davidson - Human Resource Business Partner, Josie Frawley - Executive Officer & Media team | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Broaden our advertising base, actively encouraging diversity in candidates and ensure that the recruitment process and interview panels are balanced. | Ongoing | Apply a gender lens to all advertising of positions & Look at the language used around flexibility to encourage women to apply and negotiate flexibility confidently | Success can be measured by diversifying advertising strategies, developing inclusive position descriptions, actively encouraging diversity, ensuring a balanced recruitment process with a balance recruitment panel, and promotion of a culture of inclusivity. Further monitoring and analyse will ensure ongoing success. | 2022 | Paula Davidson - Human Resource Business Partner | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Thorough job analyses completed on all new and existing positions prior to advertising | Ongoing | Review recruitment policy and processes & Ask ourselves before advertising: o Does this job need to be fulltime? o Can this job be done as a job share? | Success is measured by accurate job descriptions, informed recruitment and selection processes, effective employee development, legal compliance, employee satisfaction and engagement, organisational effectiveness, continuous improvement, comprehensive documentation, and cost efficiency. Regulat evaluation against these criteria ensures the job analysis process continues to contribute positively and add value to Council. | 2022 | Paula Davidson - Human Resource Business Partner | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Challenge stigma, stereotypes of gendered roles and negative attitudes and stop assuming others are in the same situation as us. | In progress | Review relevant policies and procedures ensuring they incorporate reference to flexible work arrangements and leave options available where appropriate. Maintain and promote existing flexible work practices and working from home etc. & Provide on-going training, education and support around the prevention of violence against women, how that applies in the workplace and proactively start open and respectful conversations about prevention and what we can do as an organisation. | Success in challenging gender stereotypes is an ongoing process. Success is measured by regular evaluations using both qualitative and quantitative measures, feedback mechanisms, and ongoing education of Council's policies and procedures. A commitment to continuous improvement also contributes to sustained success. | 2022 | Paula Davidson - Human Resource Business Partner | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Challenge ‘last century’ behaviour and encourage diversity in the workplace (e.g., ‘guys at the depot’ and ‘the girls at the front desk’) | Ongoing | Encourage traineeship and apprenticeship opportunities in gender segregated roles & Ensure images around the workplace do not promote stereotypes but rather demonstrate diversity | Images on Council publications are very neutral themed and demonstrate diversity when images of people are used. Generally, ARCC's media doesn't contain images of people (unless it is of the Mayor & community members), this way the posts on social media remain gender neutral and aim not to offend the community. Traineeships and apprenticeships are encouraged amongst all genders. Job advertisements for outdoor positions do not use gender exclusive language, therefore, aiming to encourage all to apply. However, this could be further promoted and directly encouraging women to apply may be a beneficial marketing in the future. | 2022 | Paula Davidson - Human Resource Business Partner, Josie Frawley - Executive Officer & Ian Cooper - Depot Coordinator | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
Be an ‘affirmative action’ employer to achieve a more diverse and balanced workforce. | Complete | Promote diversity and inclusion in the workplace during the entire recruitment process & Encourage different skill sets and ensure all areas of the organisation are welcoming. | A comprehensive evaluation of the success of initiatives promoting diversity and inclusion in the workplace involved analysing key indicators at each stage of the recruitment process, assessing skill set diversity, and measuring the overall atmosphere within the organisation. By continuously monitoring and adapting strategies based on these evaluations, Council can ensure sustained progress towards building a diverse and inclusive workplace. | 2022 | Paula Davidson - Human Resource Business Partner & All senior staff | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
Select one
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1: Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | 2022 | People and Culture Corporate Support | bar: Relevant indicator(s) 1 to Relevant indicator(s) 3; Relevant indicator(s) 5 to Relevant indicator(s) 7

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
The strategies and measures in ARCC's GEAP are ultimately implemented by two FTE - Paula Davidson (Human Resources Business Partner) and Josie Frawley (Executive Officer). These staff members have various other roles, responsibilities and priorities within their roles, Paula being the only HR staff member for the entire organisation and Josie covering various roles including events, community grants, Councillors diary and various other tasks. All senior staff are responsible for implementing the actions appointed to them within the GEAP, however, a large majority of these strategies are designated to minimal staff. Due to the small number of staff we have for quite a large small rural council, it has made it difficult to focus soley on implementing the actions outlined in the GEAP, there have been many conflicting priorites that have required the two responsible staff members to shift their focus to other tasks. ARCC have applied for funding through the Free from Violence Local Government Funding to employ a fulltime employee that focuses solely on crucial topics such as: gender equality, domesitc violence, fair access policies/procedures etc. This will enable a single staff member to delegate, administer, monitior and help implement these important aspects within our workplace. A stonger focus organisational wide needs to be embedded to ensure we are making significant progress in these areas.

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | Yes | While the gender composition overall has shifted in a negative direction, the reporting levels to the CEO have improved even though upon first impressions it appears to skewed. Upon deeper analysis, the following improvements have been identified: Level -1 has changed to negative as the woman in this position has taken up a position in State Government, while the Casual woman has now moved to FTT; Level -2.Both FTT women resigned to positions in the city. PTT - 2 women retired and 1 went to FTO, Casual went to FTO; Level -3 - FTT now FTO, while another resigned to the health sector. PTO and C is now dramatically lower as Council no longer provide home support services. PTT funded position ceased; Level -4 FTT went to FTO, PTT went to PTO, while one casual person had the year off to travel but is still employed. Overall this has seen a growth in the number of women in permanent ongoing roles across the organisation. | Yes | Yes | No | Yes | No | No | No
Gender composition of governing bodies | No | Council hasn't had an election since the last audit was completed, so the governing body is still made up by the same people. However, the mayor who is a woman has been re-elected for another term. | No | No | No | No | No | No | No
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | Yes | The median base salary for 2023 had a 7.1% swing and now see women paid $102.00 for every $100.00 paid to men. The mean base salary had a 5.2% swing with women now paid $103 to every $100 paid to men. The Median Total Remuneration Pay Gap = -.07% ($101 for every $100) and the Mean Total Remuneration Pay Gap = -2.2% ($102 for every $100). ARCC has worked hard to ensure that everyone is paid equally for the same work across the organisation.
Sexual harassment in the workplace | Yes | A Prevention of Sexual Harassment in the Workplace Policy/Procedure was developed and implemented across the organisation, and has been widely accepted by everyone. According to the PMS, incidents of sexual harrasment towards women has decreased between 2021 - 2023 by 4%, but has increased by 4% towards men. The upsetting factor is that none of these incidents were reported to anybody, additional research will need to be undertaken to discover the potential factors that are holding victims back from reporting. | No | No | No | No | No | No | No
Recruitment and promotion practices in the workplace | No | Council's 2021 audit data showed an even split of promotions between men and women at 50/50. These promotions occurred in middle and higher levels of the organisation. While our 2023 progress audit showed that 54% of all promotions were awarded to women, an increase of 5%. These mostly occurred in the higher levels of the organisation and were ongoing permanent roles. In our 2021 audit, women represented only 59% of new recruits in the year to 30 June 2021. However in our 2023 progress audit, this rose decreased to 44%. In 2021, of the women we recruited, 5% were employed on a full-time permanent basis, 5% on a part-time permanent basis and 15% on fixed-term contracts. The remaining new recruits were employed as casual lifeguards, predominantly juniors, at our Fitness Centre. In 2023, 7.4% of women recruited were employed on a full-time permanent basis, 7.4% on a part-time permanent basis and 3.7% on fixed-term contracts. We were not able to collect non-binary or gender-diverse data in the 2021 or 2023 periods. Our employee and payroll systems have since been updated to collect improved gender-diverse data in future years.
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | ARCC provides a number of flexible working arrangements and leave. In addition to flexible work arrangements, Council also provides access to family violence leave, gender transition leave, cultural and ceremonial leave. We have also increased our parental leave entitlements to 17 weeks for primary caregiver and 4 weeks for the secondary caregiver and included additional leave entitlements IVF leave, Adoption/Permanent Care leave, Pre-natal leave, and surrogace leave. Flexible working arrangements across the organisation is fairly balanced. Of all employees on a FWA 43% of them in 2023 are men (9% in 2021). This can be attributed to the shifting mindset of women as the primary caregiver of the family. ARCC is very supportive of all employees as caregivers.
Gendered segregation within the workplace | No | The ARCC workplace is still extremely segregated. Compared to 2021, women in management roles has decreased 16% to 40%, professional women has decreased 6% to 69%, which is still much greater than the number of professional men in the organisation. There has been no improvement amongst technicians/trades decreasing 4% to 0%. Administrative roles is still very much a female perceived role increasing to 93% in 2023. Whilst minimal, there have been improvement within machinery operators and labourers, with the latter increasing to 17% (from 0% 2021) and the latter up 3% to 14%. Albeit a slow change, ARCC is working hard to break down stereotypes about what is traditionally considered "womens work" and "mens work".
Example(s)
Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  | a | b | c | d | e | f | g
Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Relevant indicator(s) 1: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | bar: Relevant indicator(s) 1 to Relevant indicator(s) 3; Relevant indicator(s) 5 to Relevant indicator(s) 7
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled